## Sheet1
190.015 AML Projects Work Plan
|  | Research Questions & Expected Results | Single Person | Team of Two | Team of Three | Team of Four
Topic | Expected Workload 6*25=150h, where 1st week was 30h |  | 120 | 180 | 240 | 300
| Project Description, Motivation & Related Work |  | 20
Steel Production
| Access and prepare the data for ML applications |  | 16
Data | Create Histogramms |  | 8 | 16
| Analyze the correlations (e.g, scatter plots) |  |  |  | 24
| Preprocess the data (clearning) |  | 16
| Create augmented datasets (e.g., through adding noise) |  |  |  |  | 24
| Prepare Figures & Tables (raw data, erros, statistics) to Validate the models |  | 20 |  |  | 20
| Model I & hyperparameter tuning & Evaluation & Comparison |  | 40
| Model II & hyperparameter tuning & Evaluation & Comparison |  |  | 44
| Model III & hyperparameter tuning & Evaluation & Comparison |  |  |  | 20
| Evaluate the influence of the training data size |  |  |  | 16 | 16
| Total Workload |  | 120 | 180 | 240 | 300
| Project Description, Motivation & Related Work |  | 20
Mechanical Engineering
| Access and prepare the data for ML applications |  | 16
Data | Spearate into training and test sets |  | 8
| Analyze the correlations (e.g, scatter plots, statistics) |  |  | 16 | 24
| Preprocess the data (clearning) |  | 16
| Create augmented datasets (e.g., through adding noise) |  |  |  |  | 24
| Prepare Figures & Tables (raw data, erros, statistics) to Validate the models |  | 20 |  |  | 20
| Model I & hyperparameter tuning & Evaluation & Comparison |  | 40
| Model II & hyperparameter tuning & Evaluation & Comparison |  |  | 44
| Model III & hyperparameter tuning & Evaluation & Comparison |  |  |  | 20
| Evaluate the influence of the training data size |  |  |  | 16 | 16
| Total Workload |  | 120 | 180 | 240 | 300
| Project Description, Motivation & Related Work |  | 30
Robotics 1
| Setup a development framework with ROS |  | 20
LLMs & Planning | Analyze and understand the existing code |  | 10
| Integrate a person/obj detection model |  |  | 24
| Implement Facial Recognition |  |  |  | 32
| Develop a Feedback Engine to interact with people around |  |  |  |  | 40
| Prepare Figures, Tables & Videos to Validate the models |  | 20 |  |  | 20
| Evaluate the existing path planning model |  | 40
| Path planning model II & hyperparameter tuning & Evaluation & Comparison |  |  | 36
| Path planning model III & hyperparameter tuning & Evaluation & Comparison |  |  |  | 28
| Total Workload |  | 120 | 180 | 240 | 300
| Project Description, Motivation & Related Work |  | 20
Robotics 2
| Access and prepare the data for DL applications |  | 16
Mapping | Spearate into training and test sets |  | 8
| Preprocess the data (clearning) |  | 8
| Create visualization tools to visualize the image data |  | 8 | 16 | 20 | 20
| Prepare Figures & Tables (raw data, erros, statistics) to Validate the models |  | 8
| Model I & hyperparameter tuning & Evaluation & Comparison |  | 52
| Model II & hyperparameter tuning & Evaluation & Comparison |  |  | 44 | 40
| Integrate a person/obj detection & tracking model |  |  |  |  | 40
| Total Workload |  | 120 | 180 | 240 | 300
| Project Description, Motivation & Related Work |  | 20
Sign Language
| Access and prepare the data for DL applications |  | 16
| Spearate into training and test sets |  | 8
| Preprocess the data (clearning) |  | 8
| Create visualization tools to visualize the image data |  | 8 | 16
| Prepare Figures & Tables (raw data, erros, statistics) to Validate the models |  | 8
| Model I - CNN & hyperparameter tuning & Evaluation |  | 52
| Model II - Self Supervised Learning Method & Evaluation |  |  | 44
| Model II - Real-world application using a web cam & Vidoes |  |  |  | 60
| Model III - Sign Language Competition & Evaluation |  |  |  |  | 60
| Total Workload |  | 120 | 180 | 240 | 300